## Gantt chart
Project work plan
Peak Deconvolution | [13 empty] | 15 weeks · midterm in week 8
Work packages and weekly project schedule
Project schedule
WORK BREAKDOWN |  | WEEKS 1–4 |  |  |  | WEEKS 5–8 |  |  |  | WEEKS 9–12 |  |  |  | WEEKS 13–15
WP No. | Work package / task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | WEEK | WEEK | PRESENTATION | WEEK | PRESENTATION | WEEK | PRESENTATION | MIDTERM | WEEK | PRESENTATION | WEEK | PRESENTATION | WEEK | PRESENTATION | WEEK
WP1 | Local Dataset Acquisition | bar: WEEKS 1–4 2 to WEEKS 5–8 6
WP1.1 | Experimental design and dataset specification | WEEKS 1–4 2: BME+EEE; WEEKS 1–4 3: BME+EEE
WP1.2 | Solution and experimental condition preparation | WEEKS 1–4 2: BME lead; WEEKS 1–4 3: BME lead; WEEKS 1–4 4: BME lead
WP1.3 | Voltammetric measurements | WEEKS 1–4 2: BME lead; WEEKS 1–4 3: BME lead; WEEKS 1–4 4: BME lead; WEEKS 5–8 5: BME lead; WEEKS 5–8 6: BME lead
WP1.4 | Measurement quality control, labelling and dataset organisation | WEEKS 1–4 3: BME lead; WEEKS 1–4 4: BME lead; WEEKS 5–8 5: BME lead; WEEKS 5–8 6: BME lead
WP2 | Existing Dataset Preparation and Preprocessing | bar: WEEKS 1–4 2 to WEEKS 1–4 3
WP2.1 | Data, analyte information and target label review | WEEKS 1–4 2: BME lead
WP2.2 | Training, validation and test split definition | WEEKS 1–4 2: EEE lead; WEEKS 1–4 3: EEE lead
WP2.3 | Preprocessing pipeline preparation and validation | WEEKS 1–4 2: EEE lead; WEEKS 1–4 3: EEE lead
WP3 | Model Development and Evaluation | bar: WEEKS 1–4 2 to WEEKS 5–8 7
WP3.1 | Detection | WEEKS 1–4 2: EEE lead; WEEKS 1–4 3: EEE lead; WEEKS 1–4 4: EEE lead
|  |  | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML
WP3.2 | Quantification — concentration classification | WEEKS 1–4 4: EEE lead; WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead
[5 empty] | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML
WP3.3 | Quantification — concentration regression | WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead
[6 empty] | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML
WP3.4 | Model comparison and pipeline finalisation | WEEKS 5–8 7: BME+EEE
WP4 | Model Adaptation and Evaluation on Local Data | bar: WEEKS 5–8 5 to WEEKS 5–8 7; WEEKS 9–12 9 to WEEKS 13–15 14
WP4.1 | New-data preparation, splitting and preprocessing | WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead
WP4.2 | Detection pipeline adaptation and retraining | WEEKS 9–12 9: EEE lead; WEEKS 9–12 10: EEE lead
[10 empty] | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML
WP4.3 | Quantification — classification pipeline adaptation and retraining | WEEKS 9–12 9: EEE lead; WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead
[10 empty] | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML
WP4.4 | Quantification — regression pipeline adaptation and retraining | WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead
[11 empty] | T1 DL ¦ T2 ML | T1 DL ¦ T2 ML
WP4.5 | Result evaluation and comparison | WEEKS 9–12 12: BME+EEE; WEEKS 13–15 13: BME+EEE; WEEKS 13–15 14: BME+EEE
WP5 | Explainable AI (XAI) | bar: WEEKS 1–4 3 to WEEKS 5–8 7; WEEKS 9–12 9 to WEEKS 13–15 15
WP5.1 | Detection XAI — setup, explanations and reliability tests | WEEKS 1–4 3: EEE lead; WEEKS 1–4 4: EEE lead
WP5.2 | Classification XAI — explanations and reliability tests | WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead
WP5.3 | Regression XAI — explanations and reliability tests | WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead
WP5.4 | Local-data XAI — explanations and reliability tests | WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead; WEEKS 9–12 12: EEE lead
WP5.5 | Cross-task comparison of explanations | WEEKS 13–15 13: BME+EEE; WEEKS 13–15 14: BME+EEE; WEEKS 13–15 15: BME+EEE
WP6 | Web Interface Development and Integration | bar: WEEKS 1–4 2 to WEEKS 5–8 7; WEEKS 9–12 9 to WEEKS 13–15 15
WP6.1 | Web interface design and data upload | WEEKS 1–4 2: BME+EEE; WEEKS 1–4 3: BME+EEE; WEEKS 1–4 4: BME+EEE
WP6.2 | Pipeline integration and result visualisation | WEEKS 1–4 4: EEE lead; WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead; WEEKS 9–12 9: EEE lead; WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead; WEEKS 9–12 12: EEE lead
WP6.3 | Chatbot integration (result queries) | WEEKS 9–12 11: EEE lead; WEEKS 9–12 12: EEE lead
WP6.4 | End-to-end testing and documentation | WEEKS 13–15 13: BME+EEE; WEEKS 13–15 14: BME+EEE; WEEKS 13–15 15: BME+EEE
BME lead: BME primary, EEE support · EEE lead: EEE primary, BME support · BME+EEE: shared. Roles apply within both teams. Modelling cells: Team 1 / DL, Team 2 / ML (DL deep learning, ML conventional machine learning). Heading bars summarise scheduled activity; ◆ marks the planned final week. Amber week numbers: our presentation weeks (3, 5, 7, 10, 12, 14). Blank cells: no planned activity. WP6.3 chatbot: single task, result queries only. Thick-edged cell: fixed delivery week.
Project teams
|  | Department | Team 1 |  | Team 2
|  | BME | Sıla Elif Kocasaraç |  | Hıba Berchane
|  | EEE | Batu Arıbakır |  | Hasan Oruçlar
|  | Packages | ■ WP1 · Acquisition |  | ■ WP4 · Adaptation |  | ■ WP6 · Interface
|  |  | ■ WP2 · Preprocessing |  | ■ WP5 · XAI
■ WP3 · Models
|  | Owners | ■ BME lead | ▣ EEE lead | ▨ BME + EEE
|  | Delivery |  | fixed delivery week — teams may rearrange the earlier weeks of a task, not this one

## Team 1 · DL
Project work plan
Peak Deconvolution | [13 empty] | 15 weeks · midterm in week 8
Work packages and weekly project schedule · Team 1 (DL)
Project schedule · Team 1
WORK BREAKDOWN |  | WEEKS 1–4 |  |  |  | WEEKS 5–8 |  |  |  | WEEKS 9–12 |  |  |  | WEEKS 13–15
WP No. | Work package / task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | WEEK | WEEK | PRESENTATION | WEEK | PRESENTATION | WEEK | PRESENTATION | MIDTERM | WEEK | PRESENTATION | WEEK | PRESENTATION | WEEK | PRESENTATION | WEEK
WP1 | Local Dataset Acquisition | bar: WEEKS 1–4 2 to WEEKS 5–8 6
WP1.1 | Experimental design and dataset specification | WEEKS 1–4 2: BME+EEE; WEEKS 1–4 3: BME+EEE
WP1.2 | Solution and experimental condition preparation | WEEKS 1–4 2: BME lead; WEEKS 1–4 3: BME lead; WEEKS 1–4 4: BME lead
WP1.3 | Voltammetric measurements | WEEKS 1–4 2: BME lead; WEEKS 1–4 3: BME lead; WEEKS 1–4 4: BME lead; WEEKS 5–8 5: BME lead; WEEKS 5–8 6: BME lead
WP1.4 | Measurement quality control, labelling and dataset organisation | WEEKS 1–4 3: BME lead; WEEKS 1–4 4: BME lead; WEEKS 5–8 5: BME lead; WEEKS 5–8 6: BME lead
WP2 | Existing Dataset Preparation and Preprocessing | bar: WEEKS 1–4 2 to WEEKS 1–4 3
WP2.1 | Data, analyte information and target label review | WEEKS 1–4 2: BME lead
WP2.2 | Training, validation and test split definition | WEEKS 1–4 2: EEE lead; WEEKS 1–4 3: EEE lead
WP2.3 | Preprocessing pipeline preparation and validation | WEEKS 1–4 2: EEE lead; WEEKS 1–4 3: EEE lead
WP3 | Model Development and Evaluation | bar: WEEKS 1–4 2 to WEEKS 5–8 7
WP3.1 | Detection | WEEKS 1–4 2: EEE lead; WEEKS 1–4 3: EEE lead; WEEKS 1–4 4: EEE lead
|  |  | Team 1 · DL | Team 1 · DL | Team 1 · DL
WP3.2 | Quantification — concentration classification | WEEKS 1–4 4: EEE lead; WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead
[5 empty] | Team 1 · DL | Team 1 · DL | Team 1 · DL
WP3.3 | Quantification — concentration regression | WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead
[6 empty] | Team 1 · DL | Team 1 · DL | Team 1 · DL
WP3.4 | Model comparison and pipeline finalisation | WEEKS 5–8 7: BME+EEE
WP4 | Model Adaptation and Evaluation on Local Data | bar: WEEKS 5–8 5 to WEEKS 5–8 7; WEEKS 9–12 9 to WEEKS 13–15 14
WP4.1 | New-data preparation, splitting and preprocessing | WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead
WP4.2 | Detection pipeline adaptation and retraining | WEEKS 9–12 9: EEE lead; WEEKS 9–12 10: EEE lead
[10 empty] | Team 1 · DL | Team 1 · DL
WP4.3 | Quantification — classification pipeline adaptation and retraining | WEEKS 9–12 9: EEE lead; WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead
[10 empty] | Team 1 · DL | Team 1 · DL | Team 1 · DL
WP4.4 | Quantification — regression pipeline adaptation and retraining | WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead
[11 empty] | Team 1 · DL | Team 1 · DL
WP4.5 | Result evaluation and comparison | WEEKS 9–12 12: BME+EEE; WEEKS 13–15 13: BME+EEE; WEEKS 13–15 14: BME+EEE
WP5 | Explainable AI (XAI) | bar: WEEKS 1–4 3 to WEEKS 5–8 7; WEEKS 9–12 9 to WEEKS 13–15 15
WP5.1 | Detection XAI — setup, explanations and reliability tests | WEEKS 1–4 3: EEE lead; WEEKS 1–4 4: EEE lead
WP5.2 | Classification XAI — explanations and reliability tests | WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead
WP5.3 | Regression XAI — explanations and reliability tests | WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead
WP5.4 | Local-data XAI — explanations and reliability tests | WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead; WEEKS 9–12 12: EEE lead
WP5.5 | Cross-task comparison of explanations | WEEKS 13–15 13: BME+EEE; WEEKS 13–15 14: BME+EEE; WEEKS 13–15 15: BME+EEE
WP6 | Web Interface Development and Integration | bar: WEEKS 1–4 2 to WEEKS 5–8 7; WEEKS 9–12 9 to WEEKS 13–15 15
WP6.1 | Web interface design and data upload | WEEKS 1–4 2: BME+EEE; WEEKS 1–4 3: BME+EEE; WEEKS 1–4 4: BME+EEE
WP6.2 | Pipeline integration and result visualisation | WEEKS 1–4 4: EEE lead; WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead; WEEKS 9–12 9: EEE lead; WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead; WEEKS 9–12 12: EEE lead
WP6.3 | Chatbot integration (result queries) | WEEKS 9–12 11: EEE lead; WEEKS 9–12 12: EEE lead
WP6.4 | End-to-end testing and documentation | WEEKS 13–15 13: BME+EEE; WEEKS 13–15 14: BME+EEE; WEEKS 13–15 15: BME+EEE
BME lead: BME primary, EEE support · EEE lead: EEE primary, BME support · BME+EEE: shared. Roles apply within both teams. Modelling cells: Team 1 / DL, Team 2 / ML (DL deep learning, ML conventional machine learning). Heading bars summarise scheduled activity; ◆ marks the planned final week. Amber week numbers: our presentation weeks (3, 5, 7, 10, 12, 14). Blank cells: no planned activity. This sheet shows Team 1 only; the combined chart is on the first sheet. WP6.3 chatbot: single task, result queries only. Thick-edged cell: fixed delivery week.
Project teams
|  | Department | Team 1
|  | BME | Sıla Elif Kocasaraç
|  | EEE | Batu Arıbakır
|  | Packages | ■ WP1 · Acquisition |  | ■ WP4 · Adaptation |  | ■ WP6 · Interface
|  |  | ■ WP2 · Preprocessing |  | ■ WP5 · XAI
■ WP3 · Models
|  | Owners | ■ BME lead | ▣ EEE lead | ▨ BME + EEE
|  | Delivery |  | fixed delivery week — teams may rearrange the earlier weeks of a task, not this one

## Team 2 · ML
Project work plan
Peak Deconvolution | [13 empty] | 15 weeks · midterm in week 8
Work packages and weekly project schedule · Team 2 (ML)
Project schedule · Team 2
WORK BREAKDOWN |  | WEEKS 1–4 |  |  |  | WEEKS 5–8 |  |  |  | WEEKS 9–12 |  |  |  | WEEKS 13–15
WP No. | Work package / task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | WEEK | WEEK | PRESENTATION | WEEK | PRESENTATION | WEEK | PRESENTATION | MIDTERM | WEEK | PRESENTATION | WEEK | PRESENTATION | WEEK | PRESENTATION | WEEK
WP1 | Local Dataset Acquisition | bar: WEEKS 1–4 2 to WEEKS 5–8 6
WP1.1 | Experimental design and dataset specification | WEEKS 1–4 2: BME+EEE; WEEKS 1–4 3: BME+EEE
WP1.2 | Solution and experimental condition preparation | WEEKS 1–4 2: BME lead; WEEKS 1–4 3: BME lead; WEEKS 1–4 4: BME lead
WP1.3 | Voltammetric measurements | WEEKS 1–4 2: BME lead; WEEKS 1–4 3: BME lead; WEEKS 1–4 4: BME lead; WEEKS 5–8 5: BME lead; WEEKS 5–8 6: BME lead
WP1.4 | Measurement quality control, labelling and dataset organisation | WEEKS 1–4 3: BME lead; WEEKS 1–4 4: BME lead; WEEKS 5–8 5: BME lead; WEEKS 5–8 6: BME lead
WP2 | Existing Dataset Preparation and Preprocessing | bar: WEEKS 1–4 2 to WEEKS 1–4 3
WP2.1 | Data, analyte information and target label review | WEEKS 1–4 2: BME lead
WP2.2 | Training, validation and test split definition | WEEKS 1–4 2: EEE lead; WEEKS 1–4 3: EEE lead
WP2.3 | Preprocessing pipeline preparation and validation | WEEKS 1–4 2: EEE lead; WEEKS 1–4 3: EEE lead
WP3 | Model Development and Evaluation | bar: WEEKS 1–4 2 to WEEKS 5–8 7
WP3.1 | Detection | WEEKS 1–4 2: EEE lead; WEEKS 1–4 3: EEE lead; WEEKS 1–4 4: EEE lead
|  |  | Team 2 · ML | Team 2 · ML | Team 2 · ML
WP3.2 | Quantification — concentration classification | WEEKS 1–4 4: EEE lead; WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead
[5 empty] | Team 2 · ML | Team 2 · ML | Team 2 · ML
WP3.3 | Quantification — concentration regression | WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead
[6 empty] | Team 2 · ML | Team 2 · ML | Team 2 · ML
WP3.4 | Model comparison and pipeline finalisation | WEEKS 5–8 7: BME+EEE
WP4 | Model Adaptation and Evaluation on Local Data | bar: WEEKS 5–8 5 to WEEKS 5–8 7; WEEKS 9–12 9 to WEEKS 13–15 14
WP4.1 | New-data preparation, splitting and preprocessing | WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead
WP4.2 | Detection pipeline adaptation and retraining | WEEKS 9–12 9: EEE lead; WEEKS 9–12 10: EEE lead
[10 empty] | Team 2 · ML | Team 2 · ML
WP4.3 | Quantification — classification pipeline adaptation and retraining | WEEKS 9–12 9: EEE lead; WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead
[10 empty] | Team 2 · ML | Team 2 · ML | Team 2 · ML
WP4.4 | Quantification — regression pipeline adaptation and retraining | WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead
[11 empty] | Team 2 · ML | Team 2 · ML
WP4.5 | Result evaluation and comparison | WEEKS 9–12 12: BME+EEE; WEEKS 13–15 13: BME+EEE; WEEKS 13–15 14: BME+EEE
WP5 | Explainable AI (XAI) | bar: WEEKS 1–4 3 to WEEKS 5–8 7; WEEKS 9–12 9 to WEEKS 13–15 15
WP5.1 | Detection XAI — setup, explanations and reliability tests | WEEKS 1–4 3: EEE lead; WEEKS 1–4 4: EEE lead
WP5.2 | Classification XAI — explanations and reliability tests | WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead
WP5.3 | Regression XAI — explanations and reliability tests | WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead
WP5.4 | Local-data XAI — explanations and reliability tests | WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead; WEEKS 9–12 12: EEE lead
WP5.5 | Cross-task comparison of explanations | WEEKS 13–15 13: BME+EEE; WEEKS 13–15 14: BME+EEE; WEEKS 13–15 15: BME+EEE
WP6 | Web Interface Development and Integration | bar: WEEKS 1–4 2 to WEEKS 5–8 7; WEEKS 9–12 9 to WEEKS 13–15 15
WP6.1 | Web interface design and data upload | WEEKS 1–4 2: BME+EEE; WEEKS 1–4 3: BME+EEE; WEEKS 1–4 4: BME+EEE
WP6.2 | Pipeline integration and result visualisation | WEEKS 1–4 4: EEE lead; WEEKS 5–8 5: EEE lead; WEEKS 5–8 6: EEE lead; WEEKS 5–8 7: EEE lead; WEEKS 9–12 9: EEE lead; WEEKS 9–12 10: EEE lead; WEEKS 9–12 11: EEE lead; WEEKS 9–12 12: EEE lead
WP6.3 | Chatbot integration (result queries) | WEEKS 9–12 11: EEE lead; WEEKS 9–12 12: EEE lead
WP6.4 | End-to-end testing and documentation | WEEKS 13–15 13: BME+EEE; WEEKS 13–15 14: BME+EEE; WEEKS 13–15 15: BME+EEE
BME lead: BME primary, EEE support · EEE lead: EEE primary, BME support · BME+EEE: shared. Roles apply within both teams. Modelling cells: Team 1 / DL, Team 2 / ML (DL deep learning, ML conventional machine learning). Heading bars summarise scheduled activity; ◆ marks the planned final week. Amber week numbers: our presentation weeks (3, 5, 7, 10, 12, 14). Blank cells: no planned activity. This sheet shows Team 2 only; the combined chart is on the first sheet. WP6.3 chatbot: single task, result queries only. Thick-edged cell: fixed delivery week.
Project teams
|  | Department | Team 2
|  | BME | Hıba Berchane
|  | EEE | Hasan Oruçlar
|  | Packages | ■ WP1 · Acquisition |  | ■ WP4 · Adaptation |  | ■ WP6 · Interface
|  |  | ■ WP2 · Preprocessing |  | ■ WP5 · XAI
■ WP3 · Models
|  | Owners | ■ BME lead | ▣ EEE lead | ▨ BME + EEE
|  | Delivery |  | fixed delivery week — teams may rearrange the earlier weeks of a task, not this one

## Task overview
Task overview
The same tasks, timing and department assignments for both teams, without the weekly grid.
WP No. | Task | Weeks | Duration | Owner
WP1 · Local Dataset Acquisition
WP1.1 | Experimental design and dataset specification | Weeks 2–3 | 2 | BME+EEE
WP1.2 | Solution and experimental condition preparation | Weeks 2–4 | 3 | BME lead
WP1.3 | Voltammetric measurements | Weeks 2–6 | 5 | BME lead
WP1.4 | Measurement quality control, labelling and dataset organisation | Weeks 3–6 | 4 | BME lead
WP2 · Existing Dataset Preparation and Preprocessing
WP2.1 | Data, analyte information and target label review | Week 2 | 1 | BME lead
WP2.2 | Training, validation and test split definition | Weeks 2–3 | 2 | EEE lead
WP2.3 | Preprocessing pipeline preparation and validation | Weeks 2–3 | 2 | EEE lead
WP3 · Model Development and Evaluation
WP3.1 | Detection | Weeks 2–4 | 3 | EEE lead Team 1 · DL ¦ Team 2 · ML
WP3.2 | Quantification — concentration classification | Weeks 4–6 | 3 | EEE lead Team 1 · DL ¦ Team 2 · ML
WP3.3 | Quantification — concentration regression | Weeks 5–7 | 3 | EEE lead Team 1 · DL ¦ Team 2 · ML
WP3.4 | Model comparison and pipeline finalisation | Week 7 | 1 | BME+EEE
WP4 · Model Adaptation and Evaluation on Local Data
WP4.1 | New-data preparation, splitting and preprocessing | Weeks 6–7 | 2 | EEE lead
WP4.2 | Detection pipeline adaptation and retraining | Weeks 9–10 | 2 | EEE lead Team 1 · DL ¦ Team 2 · ML
WP4.3 | Quantification — classification pipeline adaptation and retraining | Weeks 9–11 | 3 | EEE lead Team 1 · DL ¦ Team 2 · ML
WP4.4 | Quantification — regression pipeline adaptation and retraining | Weeks 10–11 | 2 | EEE lead Team 1 · DL ¦ Team 2 · ML
WP4.5 | Result evaluation and comparison | Weeks 12–14 | 3 | BME+EEE
WP5 · Explainable AI (XAI)
WP5.1 | Detection XAI — setup, explanations and reliability tests | Weeks 3–4 | 2 | EEE lead
WP5.2 | Classification XAI — explanations and reliability tests | Weeks 5–6 | 2 | EEE lead
WP5.3 | Regression XAI — explanations and reliability tests | Weeks 6–7 | 2 | EEE lead
WP5.4 | Local-data XAI — explanations and reliability tests | Weeks 10–12 | 3 | EEE lead
WP5.5 | Cross-task comparison of explanations | Weeks 13–15 | 3 | BME+EEE
WP6 · Web Interface Development and Integration
WP6.1 | Web interface design and data upload | Weeks 2–4 | 3 | BME+EEE
WP6.2 | Pipeline integration and result visualisation | Weeks 4–7, Weeks 9–12 | 8 | EEE lead
WP6.3 | Chatbot integration (result queries) | Weeks 11–12 | 2 | EEE lead
WP6.4 | End-to-end testing and documentation | Weeks 13–15 | 3 | BME+EEE